## Grp4
Name | topics | Task-1 | Task-2 | Important things to keep in mind | Deadline 1 | Deadline 2 | Deadline 1 Status | Deadline 2 Status | Number of hours | Number of hours
Rishvanth | Database Architecture, JWT Authentication | Final Auth + Customer schema | JWT structure |  | 2026-08-28 | 2026-08-30 | Completed | Completed | 5 | 4 | Summary
Rishvanth |  | PK/FK relationships | Token generation |  | 2026-08-22 | 2026-08-29 | Completed | Completed | 3 | 2
Rishvanth |  | Constraints and uniqueness | Claims (user_id, role, etc.) |  | 2026-08-21 | 2026-08-30 | Completed | Completed | 2 | 1
Rishvanth |  | Audit columns | JWT validation |  | 2026-08-25 | 2026-08-27 | Completed | Completed | 1 | 4
Rishvanth |  | Integration with other teams' databases | Authentication filter |  | 2026-09-03 | 2026-08-28 | Ongoing | Completed | 2 | 1
Rishvanth |  | ER diagram | Token expiry |  | 2026-08-22 | 2026-08-30 | Completed | Completed | 1 | 0.5
Rishvanth |  | DB integration strategy | Stateless authentication |  | 2026-08-28 | 2026-08-30 | Completed | Completed | 3 | 0.5
Rishvanth |  |  | Spring Security integration |  |  | 2026-09-01 |  | Completed |  | 0.5
[11 empty] | Rishvanth | DB Design + JWT Authentication
Prakhar | Complete L1 registration implementation | Registration request/response DTOs | Database merging |  | 2026-08-29 | 2026-08-25 | Completed | Completed | 3 | 3
Prakhar |  | POST /api/register | ER diagram |  | 2026-08-27 | 2026-08-26 | Completed | Completed | 1 | 1
Prakhar |  | Controller | Integration |  | 2026-08-26 | 2026-09-03 | Completed | Ongoing | 2 | 3
Prakhar |  | Service layer |  |  | 2026-08-28 |  | Completed |  | 1
Prakhar |  | Repository interaction |  |  | 2026-08-28 |  | Completed |  | 1
Prakhar |  | Username uniqueness check |  |  | 2026-08-28 |  | Completed |  | 0.5
Prakhar |  | Email validation |  |  | 2026-08-28 |  | Completed |  | 0.5
Prakhar |  | Save user |  |  | 2026-08-28 |  | Completed |  | 0.5
Prakhar |  | Success/error response |  |  | 2026-08-28 |  | Completed |  | 3
[11 empty] | Prakhar | User Registration API
Aditya | Password Security, Everything related to securely handling passwords | BCrypt configuration | Database merging | The manual explicitly requires BCrypt with salt and provides the PasswordEncoder configuration using BCryptPasswordEncoder. | 2026-08-27 | 2026-08-25 | Completed | Completed | 2 | 3
Aditya |  | Password hashing | ER diagram |  | 2026-08-27 | 2026-08-26 | Completed |  | 1 | 1
Aditya |  | Salt handling through BCrypt | Integration |  | 2026-08-27 | 2026-09-03 | Completed |  | 0.5 | 3
Aditya |  | Never storing plaintext passwords |  |  | 2026-08-27 |  | Completed |  | 0.5
Aditya |  | Password verification |  |  | 2026-08-28 |  | Completed |  | 1
Aditya |  | Password change |  |  | 2026-08-30 |  | Completed |  | 1
Aditya |  | Password validation rules |  |  | 2026-09-01 |  | Completed |  | 1
[11 empty] | Aditya | BCrypt + Password Security
Kreshiv | Login & Account Security, The actual credential authentication before JWT | POST /api/login | Final database reverse engineered relationship diagram |  | 2026-08-29 | 2026-08-26 | Completed | Completed | 2 | 0.5
Kreshiv |  | Find user by username/email |  |  | 2026-08-27 |  | Completed |  | 0.5
Kreshiv |  | Retrieve password hash |  |  | 2026-08-27 |  | Completed |  | 0.5
Kreshiv |  | BCrypt password comparison |  |  | 2026-08-27 |  | Completed |  | 0.5
Kreshiv |  | Check account status |  |  | 2026-08-31 |  | Completed |  | 0.5
Kreshiv |  | Failed login attempts |  |  | 2026-08-31 |  | Completed |  | 1
Kreshiv |  | Account locking |  |  | 2026-09-01 |  | Ongoing |  | 1
Kreshiv |  | locked_until |  |  | 2026-09-04 |  | Ongoing |  | 1
Kreshiv |  | Reset failed attempts after successful login |  |  | 2026-09-04 |  | Ongoing |  | 0.5
Kreshiv |  | last_login_at |  |  | 2026-09-04 |  | Ongoing |  | 1
Kreshiv |  | Appropriate login error responses |  |  |  |  | Ongoing |  | 1
[11 empty] | Kreshiv | Login + Account Security
Meghna | Session & Login Audit, Security tracking after authentication | Create session after successful authentication |  |  | 2026-08-29 |  | Completed |  | 2
Meghna |  | issued_at |  |  | 2026-08-30 |  | Completed |  | 0.5
Meghna |  | expires_at |  |  | 2026-08-30 |  | Completed |  | 0.5
Meghna |  | last_activity |  |  | 2026-09-02 |  | Completed |  | 1
Meghna |  | IP address |  |  | 2026-09-02 |  | Completed |  | 1
Meghna |  | User agent |  |  | 2026-09-03 |  | Completed |  | 1
Meghna |  | Login timestamp |  |  | 2026-09-02 |  | Completed |  | 0.5
Meghna |  | Logout timestamp |  |  | 2026-09-02 |  | Completed |  | 0.5
Meghna |  | Login success/failure status |  |  | 2026-08-30 |  | Completed |  | 0.5
Meghna |  | Failure reason |  |  | 2026-09-04 |  | Completed |  | 1
Meghna |  | Logout handling |  |  | 2026-09-04 |  | Completed |  | 1
Meghna |  | Session invalidation |  |  | 2026-09-02 |  | Completed |  | 1
Meghna |  | Audit record creation |  |  | 2026-08-27 |  | Completed |  | 1
[11 empty] | Meghna | Session + Login Audit
Aastik | Auth Validation, Exception Handling & Integration, This person makes the whole authentication service production-like and testable. | API Validation |  | Exception Handling Create consistent responses for: 400 → Invalid request 401 → Invalid credentials 403 → Account disabled/unauthorized 409 → Username/email already exists 423 → Account locked 500 → Internal error Use: @Valid Bean Validation @ControllerAdvice Global Exception Handler | 2026-08-29 |  | Completed |  | 4 |  | Aasthik | Validation + Exception Handling + Integration Testing
Aastik |  | Username validation |  |  | 2026-08-31 |  | Ongoing |  | 0.5
Aastik |  | Email validation |  |  | 2026-08-31 |  | Ongoing |  | 0.5
Aastik |  | Password validation |  |  | 2026-08-26 |  | Completed |  | 1
Aastik |  | Required-field validation |  |  | 2026-09-02 |  | Ongoing |  | 1
Aastik |  | Duplicate username/email handling |  |  | 2026-09-01 |  | Completed |  | 0.5

## GROUP 8
NAME | Topic | Tasks | Status | Remarks | Deadline
Pratik | database Architecture | Design product & product_type_master tables | Completed |  | Sept 10
|  | PK/FK relationships | Completed |  | Sept 10
|  | constraints & indexes | Completed |  | Sept 10
|  | JPA entities (Product, ProductTypeMaster, ProductCharacteristic, ProductRule) | Completed |  | Sept 10
|  | Verify Flyway migration matches entities exactly | Completed |  | Sept 14
|  | fix schema/entity type mismatches | Completed |  | Sept 14
|  | export ER diagram Important: Column types must match exactly between SQL and Java (CHAR vs VARCHAR, @Lob vs TEXT both broke the build once each — double-check every type) | Completed |  | Sept 14
Arun | Database Architecture | Design product_pricing | Completed |  | Sept 10
|  | Interest rate | Completed |  | Sept 10
|  | Rate matrix | Completed |  | Sept 10
|  | Charge | Completed |  | Sept 10
|  | Product Charge | Completed |  | Sept 10
|  | Product notification table | Completed |  | Sept 10
|  | Matching JPA entities | Completed |  | Sept 14
|  | Run Flyway Migration | Completed |  | Sept 14
|  | debug schema-validation errors | Completed |  | Sept 14
|  | reverse-engineer ER diagram in MySQL Workbench | Completed |  | Sept 14
Arnav | Security | Set up SecurityConfig (open access for now) | Ongoing | Task-1's real activation is BLOCKED on the Auth group's login service being ready — mark as "waiting on Group 4" if it's not live yet | Sept 14
|  | prepare the JWT/@PreAuthorize plan for later | Ongoing |  | Sept 14
|  | Coordinate with the Login/Auth group on JWT timing | Ongoing |  | Sept 14
|  | confirm the API contract with FD Calculator & FD Account groups | Ongoing |  | Sept 14
|  | Task-1's real activation is BLOCKED on the Auth group's login service being ready — mark as "waiting on Group 4" | Ongoing |  | Sept 14
Yashovardhan | API Layer, Testing & Documentation | Build all 7 controller endpoints | Ongoing | Blocked until Prathik & Arun's DB layer is confirmed working (it now is — you can start) | Sept 14
|  | import/run Postman collection | Ongoing |  | Sept 14
|  | test each endpoint end-to-end | Ongoing |  | Sept 14
|  | Write/update API documentation | Ongoing |  | Sept 14
|  | confirm the JSON contract exactly matches what's shared with the FD Account group | Ongoing |  | Sept 14
Divyansh | Service Layer — Search, Pagination & Validation | Build ProductService business logic (create/search/update validation) | Ongoing | Same DB-dependency note as Yashovardhan | Sept 14
|  | implement pagination on the search endpoint | Ongoing |  | Sept 18
|  | Integration testing with the Postman collection | Ongoing |  | Sept 18
|  | fix any bugs found during testing | Ongoing |  | Sept 18
Anant | Category Pricing Logic | Build the add/list category-rate endpoints (senior citizen, employee, age-bracket rules) | Ongoing | The rate-capping math needs careful testing — test with 2-3 stacked categories to confirm the cap actually hold | Sept 14
|  | Build & test the effective-rate calculation (stacking multiple category adjustments, capping at rateMax) | Ongoing |  | Sept 14

## GROUP 12
NAME | TOPIC | Tasks | Deadline | Remarks | Status
Manav | Deposit Processing | Deposit API | 2026-09-02 |  | Started
|  | Deposit Business Logic | 2026-09-02 |  | Started
|  | Deposit Transaction Recording | 2026-09-02 |  | Started
Manav | Transaction Ledger | Transaction Entity and Schema | 2026-09-21 |  | Started
|  | Transaction History API | 2026-09-21 |  | Started
|  | Transaction Consistency | 2026-09-21 |  | Started
Dhruv | Interest Accrual | Interest Calculation | 2026-09-21 |  | Completed
|  | Accrual Processing | 2026-09-21 |  | Completed
|  | Interest Transaction Recording | 2026-09-21 |  | Completed
Dhruv | Interest Batch | Batch Scheduler | 2026-09-02 |  | Completed
|  | Batch Execution | 2026-09-02 |  | Completed
|  | Batch idempotency | 2026-09-02 |  | Completed
Anmol | Notification | Notification Service | 2026-09-11 |  | Started
|  | Notification Logging | 2026-09-11 |  | Started
|  | Notification Templates | 2026-09-11 |  | Started
Anmol | Reporting | FD Statement Generation | 2026-10-03 |  | Waiting for Other Modules
|  | Statement API | 2026-10-03 |  | Waiting for Other Modules
|  | Reporting Integration | 2026-10-03 |  | Waiting for Other Modules
Mayank | Withdrawal | Withdrawal Eligibility | 2026-09-02 |  | Started
|  | Interest till Withdrawal | 2026-09-02 |  | Completed
|  | Penalty Calculation | 2026-09-02 |  | Started
Mayank | Maturity and Closure | Maturity Detection | 2026-09-15 |  | Not Started
|  | Maturity Interest Calculation | 2026-09-15 |  | Not Started
|  | Account Closure | 2026-09-15 |  | Not Started
Shrey | Simulation Engine | Simulation API | 2026-09-02 |  | Completed
|  | Interest Simulation | 2026-09-02 |  | Completed
|  | Effective Rate Calculation | 2026-09-02 |  | Completed
Shrey | Role Based Service Access | Role Authorization | 2026-09-15 |  | Waiting for Other Modules
|  | Ownership Checks | 2026-09-15 |  | Waiting for Other Modules
Sai Darshith | Account Creation | Account Creation API | 2026-09-02 |  | Completed
|  | FD Account Number Generation | 2026-09-02 |  | Completed
|  | Account Initialization | 2026-09-02 |  | Completed
Sai Darshith | Frontend | FD Account UI | 2026-10-15 |  | Waiting for Other Modules
|  | WIthdrawal UI | 2026-10-15 |  | Waiting for Other Modules
|  | Calculator UI | 2026-10-15 |  | Waiting for Other Modules
|  | API Integration | 2026-10-15 |  | Waiting for Other Modules

## Absentees
2026-09-04 | 2026-09-11
Prakhar | yasho
manav
mayank